## Slide 1
Chart: Velocity Chart Sprint 7
| Monday | Tuesday | Wendsday | Thursday | Friday
Team Velocity | 0 | 4 | 2 | 3 | 8
Average Team Velocity | 3.4 | 3.4 | 3.4 | 3.4 | 3.4
Optimal Velocity | 4.4 | 4.4 | 4.4 | 4.4 | 4.4

## Slide 2
Chart: Burndown Chart Sprint 7
| Monday | Tuesday | Wendsday | Thursday | Friday
Team Burn | 22 | 18 | 16 | 13 | 5
Optimal Burn | 22 | 16.5 | 11 | 5.5 | 0

## Slide 3: Velocity vs Burndown
Velocity – how much was done
Burndown – how much has been done from the whole

## Slide 4
Chart: Velocity Chart
| Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6
Team-Velocity | 0 | 8 | 4 | 3 | 15 | 9
Begin of project
8
4
3
15
9

## Slide 5
Chart: Burn Down Chart
| Sprints
Sprint 0 | 41
Sprint 1 | 34
Sprint 2 | 30
Sprint 3 | 27
Sprint 4 | 15
Sprint 5 | 8
41
34
30
27
15
8
Notes: real

## Slide 6
Chart: Burn Down Chart
| Sprints
Sprint 0 | 41
Sprint 1 | 33
Sprint 2 | 20
Sprint 3 | 17
Sprint 4 | 14
Sprint 5 | 6
Sprint 6 | 5
Sprint 7 | 2
Notes: Estimated

## Slide 7
Chart: Use Cases
| Use Cases
US-01 | 8
US-02 | 13
US-03 | 3
US-04 | 3
US-05 | 8
US-06 | 1
US-07 | 3
US-08 | 2
Notes: Use Case workload